## Overview
SAMPLE ONLY *Modify as per your situation and timelines. Some elements are flexible while others have set parameters; refer to SGS Policies and Checklist for details. https://www.uleth.ca/education/programs-degrees/graduate-studies/culminating-activities | Year(s**) (enter) | Year (enter) | [11 empty] | Year (enter)
|  | Summer |  |  |  | Fall |  |  |  | Spring |  |  |  | Summer |  |  |  | Fall |  |  |  | Spring
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Coursework **Duration is dependent upon program, refer to cohort schedule | X | bar: Summer May to Spring Apr
Establish Supervisory Committee
Submit Establishment of Supervisory Committee (completed 4 courses minimum, including research course) | bar: Summer Jul
Submit Statement of Progress and Standing (meeting every 6 months) | bar: Fall Nov; Summer May
Project Proposal
Develop Project Proposal | bar: Summer Aug to Fall Oct
Submit Approval of Thesis Proposal form with final Thesis Proposal | bar: Fall Nov
Ethics (Not typical for Project)
Project Proposal must be approved before submitting to Human Participant Research Committee | bar: Fall Dec to Spring Jan
Research and Writing | bar: Spring Feb to Spring Apr
Review and assessment of project
Edits to written Project until Superivsory committee satisfied with final Project | bar: Summer May
Recommendation of the Award of the Degree form submitted | bar: Summer Jun
Submission of Project via e-project system | bar: Summer Jun
Request for Publication Embargo (only if needed) | bar: Summer Jun
Review and approval of Project by Associate Dean, GSR | bar: Summer Jul
Review and approval of Project by Dean, SGS | bar: Summer Jul
Apply to graduate | bar: Summer Jun
Program Complete | bar: Summer Aug
Convocation | bar: Fall Oct