## Overview
SAMPLE ONLY *Modify as per your situation and timelines. Some elements are flexible while others have set parameters; refer to SGS Policies and Checklist for details. https://www.uleth.ca/education/programs-degrees/graduate-studies/culminating-activities | Year(s**) (enter) | Year (enter) | [11 empty] | Year (enter)
|  | Summer |  |  |  | Fall |  |  |  | Spring |  |  |  | Summer |  |  |  | Fall |  |  |  | Spring
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Coursework **Duration is dependent upon program, refer to cohort schedule | X | bar: Summer May to Spring Apr
Establish Supervisory Committee
Submit Establishment of Supervisory Committee (completed 4 courses minimum, including research course) | bar: Summer Jul
Submit Statement of Progress and Standing (meeting every 6 months) | bar: Fall Nov; Summer May; Fall Nov
Thesis Proposal
Develop Thesis Proposal | bar: Summer Aug to Fall Oct
Notify GSR of Thesis Proposal defence (min. 2 weeks prior) | bar: Fall Nov
Thesis Proposal defence held | bar: Fall Nov
Submit Approval of Thesis Proposal form with final Thesis Proposal | bar: Fall Dec
Ethics
Thesis Proposal must be approved before submitting to Human Participant Research Committee | bar: Spring Jan to Spring Feb
Research and Writing | bar: Spring Mar to Summer Jul
Thesis Oral Defence
Supervisor identifies External Examiner (2 months prior to defence) | bar: Summer Aug
Submit Request for Final Thesis Examination, External's CV and Conflict of Interest, PDF of Thesis (6 wks prior to defence) | bar: Summer Aug
Approval of Final Thesis Examination Committee | bar: Summer Aug
Notice of event and communication with Committee, External, etc. | bar: Fall Sep
Review and assessment of thesis | bar: Fall Sep
Submission of Assessment of Readiness to Defend form (min. 2 wks prior to defence) | bar: Fall Sep
Thesis Oral Defence held | bar: Fall Oct
Edits to written Thesis as per Oral Defence, approved by Supervisor/Committee accordingly | bar: Fall Oct
Recommendation of the Award of the Degree form submitted | bar: Fall Nov
Submission of Thesis via e-thesis system | bar: Fall Nov
Request for Publication Embargo (only if needed) | bar: Fall Nov
Review and approval of Thesis by Associate Dean, GSR | bar: Fall Nov
Review and approval of Thesis by Dean, SGS | bar: Fall Nov
Apply to graduate | bar: Fall Oct
Program Complete | bar: Fall Dec
Convocation | bar: Spring Feb