## Overview
SAMPLE | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Courses:
Comprehensive Examination (by end of year two):
Written component of Comprehensive Examination:
Questions posed by committee and student responds (28 -35 days; see concentration)
Committee reviews written response (3 weeks)
Policy: A student who fails the written component must wait a min. of 2 weeks, to a max. of 4 months to successfully complete
Oral component of Comprehensive Examination:
Comprehensive Examination Complete
Thesis Proposal
Supervisory Committee recommends that Thesis Proposal proceeds to Proposal Defence
Two weeks prior to Proposal Defence, supervisor notifies GSO of date, time and location
Thesis Proposal Defence held
Edits to proposal as per Proposal Defence, Supervisory Committee submits Approval of Thesis Proposal
Submitted to PhD in Education Committee for preliminary review
Submitted to Dean, SGS for approval
Thesis Proposal Complete
Ethics:
Research and Writing:
Thesis Oral Defence:
Ready to defend
PDF of Thesis submitted to GSO, and Request for Final Thesis Examination Request (requires External's CV and Conflict of Interest - min. 8wks prior to defence)
Approval of Final Thesis Examination Committee
Notice of event and communication with Committee, External, etc.
Review and assessment of thesis
Submission of Examiners' Report on the Thesis to GSO (min. 2 wks prior to defence)
Thesis Oral Defence held
Edits to written Thesis as per Oral Defence, approved by Supervisor/Committee accordingly
Recommendation of the Award of the Degree form submitted
Submission of Thesis via e-thesis system
Review and approval of Thesis by Associate Dean, GSR
Review and approval of Thesis by Dean, SGS
Program Complete:
https://uleth.service-now.com/sgs